## Slide 1
ICBD Holdings:
Project Precision
Kick-off Presentation by

## Slide 2
Agenda
Project Precision : Overview
Project Scope
Workflow Architecture
Clarifications Needed
Project High Level Plan
Our Understanding
Costing

## Slide 3
Overview
© 2024 Sigmasoft All Rights Reserved
Business Challenge:​ : Revenue estimation and Accounts Receivable (AR) are currently done manually in Excel — slow, error-prone, and not auditable.
Goal:​ Automate monthly revenue estimation and make it auditable, repeatable, and faster.
Solution:​ Build a data-driven system using Snowflake + Python for calculations and Power BI for reporting
Outcome:​ Finance team will have accurate, audit-ready results by the 4th business day of each month.

## Slide 4
Project Scope
© 2024 Sigmasoft All Rights Reserved
In Scope (Phase 1):​
Build Master Rate Table (MRT) – automated calculation of rates.
Create Connect Appointment Exports with estimated revenue.
Develop Variation Report (YTD changes in revenue).
Provide CollaborateMD Transaction Export with all charges and flags.
Out of Scope (Future Phase ):​
Real-time dashboards (only CSV/Excel exports).
Automated Contract document ingestion.
Advanced calculations like patient vs insurance split.

## Slide 5
Our Understanding
© 2024 Sigmasoft All Rights Reserved
The ICDB wants a fully automated revenue estimation process that can be re-run any time with the same result (idempotent).
The system should log every step and decision, so auditors can trace how revenue numbers were calculated.
The core calculation uses historical “Allowed per Unit” data to derive a Rate per Unit (RPU) for each CPT code.
The solution must generate 5 output files each month — including Master Rate Table, Appointment Revenue, and Audit Reports.
The full data flow will move from ABAConnect (EMR) → CollaborateMD (Billing) → Snowflake → Power BI Reports.
Everything must be ready to deliver results by the 4th business day each month.
Future scope: integrate EOB documents, add predictive analytics, and build real-time dashboards later.

## Slide 6
Workflow Architecture
Notes: SmartTest is a Sigmasoft’s inhouse GenAI-powered no-code web automation testing tools streamline and enhance the automation process, merging the established automation strengths of Selenium with advanced AI features. This intuitive no-code approach enables users to automate web testing without writing any code, minimizing the need for coders..The SmartTest tool streamlines test lifecycle, achieving a 40% reduction in effort. Generate Test Cases
Our SmartTest tool intelligently analyzes requirements from sources such as user stories ,process flow , requirements shared in Word documents to automatically generate comprehensive test cases.
Build Automation Scripts
This no-code solution accelerates the execution of automation scripts, enhances testing efficiency, and provides in-depth report analysis, delivering valuable insights for continuous quality improvement.
Execute
Its self-healing capabilities adapt to changes in object locators during runtime, eliminating the need for coding expertise and ensuring consistent, accurate results. This tool not only enhances efficiency but also provides significant value by accelerating time-to-market and improving overall quality assurance.

## Slide 7
Clarifications Needed
© 2024 Sigmasoft All Rights Reserved
Data Lineage & Source: Confirm lineage, source of truth (Connect vs. Collab), and data quality issues.
Time & History: Define YTD format, time series needs, and how much historical data to process.
Pipeline & Output: Clarify if data pipelines need incremental/full refresh and confirm output format & target environment.
Business Rules: Need clarity on client–payer relationships, rate variation logic, thresholds, and outlier treatment.
Transaction Handling: Define how to handle missing CPTs, zero units, finalized or partial transactions.
Process Logic: Explain requirements for Multiplan Flag, variation tracking, and revenue recognition rules.
Technical Workflow: Provide detailed Precision environment workflow including Salesforce source layer

## Slide 8
Project High Level Plan
© 2024 Sigmasoft All Rights Reserved
Phase | Duration | Key Deliverables
Week 1–2 | Requirement finalization & data analysis | System mapping, logic sign-off
Week 3–4 | Build Snowflake data model | ETL setup, core logic
Week 5–6 | Validation, testing & automation | Audit logs, sample runs
Week 7–10 | Build Power BI Reports | Key Delivery Dashboards
Week 11–12 | Final delivery , Hypercare & handover | Export files + documentation

## Slide 9
Project Costing
© 2024 Sigmasoft All Rights Reserved
Component | Effort | Approx. Cost (USD)
Data Integration & Snowflake Setup | 3 weeks | $15 K
Logic Development (RPU, MRT, Audit) | 4 weeks | $20 K
Validation, Testing & Fixes | 2 weeks | $8 K
Power BI Reporting & Exports | 2 weeks | $6 K
Documentation & Project Management | 1 week | $4 K
Total Estimated Cost | 12 weeks | $53 K (approx.)

## Slide 10
Execution Approach
Planning & Analysis
  Assessment of the current environment
  Tableau online setup
  Data source and Workbook inventory
  User Access mapping
Migration
  Backup Tableau Server workbooks
  Prepare Structure
  Migrate Data Source
  Migrate Workbook
  Migrate Users and Group
  Set Refresh Schedule (If Any)
  Perform Initial Smoke Test
UAT
  Coordinate with business users
  Initiate UAT
  Capture feedbacks and Fix issues
  Data Sources Accessibility Testing
  Workbook Accessibility Testing
  Workbook Data Validation
  Functional Testing (Drill down, Drill through
Pre Migration Preparation
  Environment readiness
  Tableau Inventory preparation
  Data sources adjustment
  Identify dependencies
  Migration preparation, set roles & responsibilities
Testing & Validation
  Site Admin level testing
  Data Source level testing
  Workbook level testing
  Data Validation
  Functional Testing
  Schedule Extract Refresh Testing
  Subscription Testing
  Backup Testing
Go Live & Normalization
  User Support and Communication
  Continuous Monitoring
  Knowledge transfer & training
  Security Audits
1
2
3
4
5
6

## Slide 11
Project Timeline
Planning & Analysis
Pre Migration Preparation
Migration
Kick-off, Team Alignment
Phases
Project Initiation
Post Migration Validation & UAT
Go Live & Normalization
Hypercare Support
Stakeholder alignment, access provisioning, Plan finalization
29th Sep
10th Oct
Inventory, DS Mapping, Dependency mapping, RLS
Workbook & DS Migration,
User and group migration
Ffunctionality, Unit and UAT Testing. Performance Monitoring
Usage Analysis, Monitor dashboard, respond and fix the issue and Validate RLS
Feedback, Sign-off
22nd Sep
15th Sep
8th Sep
1st Sep
25th Aug
19th Aug

## Slide 12
Project Milestones
 | Project Start Date | 19th Aug 2025
 | Tentative QA Date | 08th Sep 2025 – 12th Sep 2025
 | Tentative UAT Date | 15th Sep 2025 – 18th Sep 2025
 | Tentative Go-Live Date | 19th Sep 2025
 | Hypercare Support | 29th Sep 2025 – 10th Oct 2025

## Slide 13
info@sigmasoft.ai
Head Quarters:
United States:
SSIT INC, 5201 Great America Parkway, Suite 320, Santa Clara, CA, 95054
www.sigmasoft.ai
Thank You!

## Slide 14
Team Onboard Status
Access Status Matrix | Document Sign and revert | Nvidia Confirmation mail | Yubi Key Device Status | Mail & Teams Configuration | Yubi Key Configuration | Mandatory Training Mail | Mandatory Training Status
Saurabh Pandey | Done | Received | Received | Pending | Pending | Not Received | Pending
Rinki Sehgal | Done | Received | Received | Done | Done | Received | Completed
Sivakumar Sura | Done | Received | Received | Done | Done | Received | Completed
Kunal Gajabe | Done | Received | Received | Done | Done | Received | Completed
Vengat Rajan | Done | Pending | Ordered YubiKey | Pending | Yet to Receive YubiKey device | Not Received | Pending

## Slide 15
Prerequisites & Next Steps
Access Provisioning: Environment Access
  Tableau Server
  Tableau Online
  Databricks
  Other data sources
Tableau Environment walk though
Requirement Review
Open Questions : Open Questions

## Slide 16
Elements to Test for a Migration
© 2024 Sigmasoft All Rights Reserved
Data Connection
Confirm that the data connections to Databricks or any other data source remain intact after the migration. Validate dependencies between workbooks and data sources
Refreshing Data Extracts
Force and extract to run (Instead of running it manually or waiting for it's scheduled time) and validate this in Tableau
Opening Workbooks
Can Users actually access their workbooks? Simulates user who can open a Tableau workbook.
Validate the User Experience
make sure that dashboards open and refresh at least as fast
as before, and navigation is working as expected.
Workbooks Display the same Information
Regressions are one of the highest risks in Analytics. Compare two versions of a set of dashboards across environments.
Publishing Workbooks and Data Sources
Make sure users can continue to publish workbooks and data sources.

## Slide 17
High-level
Project Plan

## Slide 18
Data Connection
Confirm that the data connections to Snowflake or any other data source remain intact after the migration. Validate dependencies between workbooks and data sources
Refreshing Data Extracts
Force and extract to run (Instead of running it manually or waiting for it's scheduled time) and validate this in Tableau
Workbooks Display the same Information
Regressions are one of the highest risks in Analytics. Compare two versions of a set of dashboards across environments.
Opening Workbooks
Can Users actually access their workbooks? Simulates user who can open a Tableau workbook.
Validate the User Experience
make sure that dashboards open and refresh at least as fast
as before, and navigation is working as expected.
Publishing Workbooks and Data Sources
Make sure users can continue to publish workbooks and data sources.
1
2
3
4
5
6
Elements to Test for a Migration
Testing Strategy Document
Reference:

## Slide 19
Sigmasoft (SSIT) NVidia Team
Role | Team | Name
Project Manager | NVidia | Nikhil Kulkarni
Client Partner | Sigmasoft (SSIT INC) | Saurabh Pandey
Delivery Head | Sigmasoft (SSIT INC) | Achutha Raju Kalvakolanu
On Site Manager | Sigmasoft (SSIT INC) | Rinki Sehgal
Tableau Architect | Sigmasoft (SSIT INC) | Vengateshwaran
Tableau Administrator | Sigmasoft (SSIT INC) | Sivakumar Sura
Tableau Developer | Sigmasoft (SSIT INC) | Kunal Gajbe

## Slide 20
Project Objective & Scope
© 2024 Sigmasoft All Rights Reserved
  1. Migration
Migration of 3 Reports/workbooks comprising dashboards and data sources from Tableau Server to Tableau Online
  2. Validation
Validation of the successful migration of data sources and workbooks, ensuring data integrity, user access, and overall functionality
  3. Migration Success
Go live and Normalization support
  Scope:

## Slide 21
Delivery Manager
- Overall project oversight - Client communication & stakeholder alignment - Risk management - Escalation point
Project Lead
- Project planning & execution - Task allocation & progress tracking - Coordination among teams - Weekly status reporting
Tableau QA
- UAT planning & test case creation - Validation of migrated content - Regression testing - Hypercare support & issue tracking
Delivery Head
Tableau Administrator
- Inventory of existing content (Workbooks, Data Sources, Users, Permissions) - Environment setup in Tableau Online - Authentication & SSO setup - Scheduling refreshes & monitoring
Tableau Developer
- Workbook validation post-migration - Performance tuning - Dashboard branding as per guidelines - Supporting enhancements during migration
Roles & Responsibilities

## Slide 22
Team Readiness
Ready team for Early Deployment
Name | Role | Experience | Experience Summary
Rinki Sehgal | On-Site Project Manger | 16 Yrs | Supply chain expert with 16 years of experience delivering data-driven solutions across ERP platforms such as SAP, Oracle, and Infor to optimize performance and efficiency.
 |  |  | Proficient in Power BI, Tableau, and end-to-end BI lifecycles—from data modeling to dashboard delivery—to support strategic decision-making.
 |  |  | Trusted by Fortune 500 clients to automate reporting, implement cloud analytics, and turn complex data into actionable business insights.
Vengateshwaran | Project Lead | 11 Yrs | BI Practice Lead Proven expertise in leading BI projects, delivering actionable insights, and supporting strategic decision-making
 |  |  | Proficient in developing interactive reports and dashboards using various BI tools
 |  |  | Specialized in Tableau, PowerBI, Data Management, Alteryx, Tableau Pulse and Tableau Prep.
 |  |  | Certified Tableau Professional
Siva Kumar S | Tableau Admin | 7 Yrs | Experience in Tableau Desktop, Tableau Server, in data analysis, reporting, and cloud data warehousing.
 |  |  | Proficient in Building dashboards in Tableau, writing complex SQL queries, and integrating data from Snowflake.
 |  |  | Expert in Data modeling, performance optimization, creating interactive visualizations, and managing Snowflake data pipelines.
 |  |  | Certified Tableau Desktop Specialist
Kunal Gajbe | Tableau Specialist | 4 Yrs | Experience Salesforce, Tableau, and Power BI in CRM, reporting, and data visualization
 |  |  | Proficient in dashboard creation in Tableau/Power BI, Salesforce customization, and business process automation.
 |  |  | Expert in building interactive, data-driven dashboards, Flow/Process Builder, and Salesforce admin tasks.
 |  |  | Certified Salesforce Administrator, Advanced Administrator, CPQ Specialist
Notes: Our team is fully prepared and equipped to deliver exceptional results, with experts, including Solution Architects ,Tech Leads, Integration experts, ensuring the highest level of expertise and leadership for successful project execution