## ICBD PoC Timeline
S. No. | Task | Start Date | End Date | Daily Remarks
1 | Project Kickoff | 2025-12-29 | 2025-12-29 | Both SSIT & ICBD team Connected and planned for Future PoC Discussion ,along with data sources Sharing
2 | Initial Questionarie & Discovery | 2026-01-06 | 2026-01-08 | ICBD team shared the Data sources Metadata information and Connected for further discussion
3 | Metadata Analysis & Initial Architecture Framework | 2026-01-09 | 2026-01-14 | ICBD & SSIT team connected on Metadata discussion and Initial Architecture Framework
4 | Detailed Architecture Design & Environment Access | 2026-01-16 | 2026-01-21 | Snowflake access to ICBD envirmnet to SSIT team has been provisioned along with detailed Architecture design sharing
5 | PoC Kickoff & Data Discussion | 2026-01-20 | 2026-01-28 | ICBD & SSIT team connected on New datasets for PoC Scope along with upcoming Datasets scope for future upgrades
6 | New Scope Discussion | 2026-01-26 | TBD | ICBD Team has initiaed discussion on New Scope & SOW for other stakeholders
7 | Data Analysis & Data Preparation | 2026-01-28 | 2026-01-30
8 | Snowflake Ingestion | 2026-02-02 | 2026-02-04
9 | Data Transformation & Mart Layer | 2026-02-04 | 2026-02-06
10 | Semantic Layer Build | 2026-02-09 | 2026-02-11
11 | Integration & Validation | 2026-02-12 | 2026-02-13
12
13

## Synopsys PoC Timeline
S. No. | Task | Start Date | End Date | Daily Remarks
1 | Project Kickoff & Architecture Review | 2026-01-22 | 2026-01-22 | The PoC Scope and Initial Architecture Framework Finalized with Jean Paul
2 | Synthetic Data Validation & Setup | 2026-01-23 | 2026-01-23 | The Synthectic Data already validated with Jean paul for PoC ,will be prepared for more rows is in Progress
3 | Environment Setup & Infrastructure Provisioning | 2026-01-23 | 2026-01-23 | The Databricks Environment Stack is selected for the PoC , The schema & Catalog prepparation is in progress
4 | Data Integration Layer Development (Synthetic Data) | 2026-01-27 | 2026-01-27
5 | Core Solution Development | 2026-01-27 | 2026-01-27
6 | Data Quality & Governance Framework | 2026-01-27 | 2026-01-27
7 | Solution Testing & QA (Synthetic Data) | 2026-01-28 | 2026-01-28
8 | Unstructured Data Integration Framework Design | 2026-01-29 | 2026-01-30
9 | Prototype Refinement Based on Feedback | 2026-02-02 | 2026-02-02
10 | Performance & Scalability Testing | 2026-02-03 | 2026-02-02
11 | POC Evaluation & Success Criteria Assessment | 2026-02-04 | 2026-02-02
12 | Documentation & Knowledge Transfer | TBD | TBD
13 | Customer & Forum Demonstrations | TBD | TBD

## Webinar Timeline
S. No. | Task | Start Date | End Date | Daily Remarks
1 | Project kickoff, assign roles, content outline, demo assessment | 2026-01-27 | 2026-01-27
2 | Script Part 1 (Intro & Platform), Databricks provisioning, TPC-H dataset, templates | 2026-01-28 | 2026-01-28
3 | Script Part 2 (Genie AI & Capabilities), Unity Catalog setup, slide template design | 2026-01-29 | 2026-01-29
4 | Script Part 3 (Governance & Dashboards), build 2 dashboards, slides mockups | 2026-01-30 | 2026-01-30
| TBD | 2026-01-31 | 2026-01-31
|  | 2026-02-01 | 2026-02-01
5 | Compile master script, & demo flow testing along with demo scenarios | 2026-02-02 | 2026-02-02
6 | Complete slides 11-20 with graphics & Internal review | 2026-02-03 | 2026-02-03
7 | Final demo run-through with scope of refinement | 2026-02-04 | 2026-02-04
8 | Script review , system health checks (cluster, network, recording) | 2026-02-05 | 2026-02-05
9 | Script updates with timings, Top 20 Q&A responses, | 2026-02-06 | 2026-02-06
| TBD | 2026-02-07 | 2026-02-07
|  | 2026-02-08 | 2026-02-08
10 | Final rehearsal mock &platform testing | 2026-02-09 | 2026-02-09
11 | LIVE WEBINAR | 2026-02-10 | 2026-02-10

## Databricks Acceleartors
S. No. | Task | Start Date | End Date | Daily Remarks
1 | Sandbox Setup & Environment Prep | 2026-01-19 | 2026-01-27 | Databricks Free editoin has been used ,we are using standard clusters and all the available offerings along with customization , already applied for increase in databricks offering for the PoC but yet to get anyy response from databricks team
2 | Requirements & Architecture Design | 2026-01-20 | 2026-01-27 | We will be using the same architecture as used in AI Log Analytics for Denodo Hackathon , will be updating with custom changes and customizable modules for other business users
3 | Data Ingestion & Source Setup | 2026-01-28 | 2026-01-30
4 | Spark Streaming & Custom Quality Logic | 2026-02-02 | 2026-02-06
5 | Feature Engineering & ML Model Development | 2026-02-09 | 2026-02-13
6 | Model Serving & Real-Time Scoring | 2026-02-16 | 2026-02-18
7 | Query Layer, Dashboards & Analytics | 2026-02-18 | 2026-02-20
8 | Integration & Scalablity Testing | 2026-02-23 | 2026-02-26
9 | Internal Team Demo | 2026-02-27 | 2026-02-27
10 | Prototype Refinement Based on Feedback | TBD | TBD